## Slide 1: CHANDIGARH SMART CITY LIMITED

## Slide 2
Potable Water & Wastewater
Pan City ICT Projects
Solid Waste Management
Urban Retrofit & Redevelopment
Mobility & Social Sector
Energy Reforms
Rs. 1486.58 Cr
Rs. 147.48 Cr
Rs. 27.02 Cr
Rs. 120.04 Cr
Rs. 149.91 Cr
Rs. 261.42 Cr
Surveys & Investigations
Situation Analysis
Feasibility
DPR
RFP/ Tender
Implementation
STAGES – PROJECT OUTPUT
MISSION OVERVIEW
Total Projects
SCP: 63
CSCL : 36
Convergence: 27
Expected Capital Investment – Rs. 1910.52 Cr
Pan City Projects
Area Based Development
Expected Capital Investment – Rs. 282.29 Cr
SECTOR
Methodology

## Slide 3
PROJECT STATUS -CSCL
7
Rs. 39.6 Cr
9
Rs. 677.8 Cr
16
Rs. 1151.33 Cr
12
Rs. 120.13 Cr
19
Rs. 203.95 Cr
63
2192.81 Cr
Notes: Projects

## Slide 4
Chart: ICT and E governance
| DPR under Preparation | DPR approved | Tender Issued | Work Order Issued | Work Completed
 | 0 | 1 | 7 | 1 | 1
 | 0 | 440 | 1041.71 | 4.05 | 0.82
Chart: Energy Sector
| DPR under Preparation | DPR approved | Tender Issued | Work Order Issued | Work Completed
 | 0 | 1 | 7 | 1 | 1
 | 0 | 440 | 1041.71 | 4.05 | 0.82
Chart: Solid Waste Management
| DPR under Preparation | DPR approved | Tender Issued | Work Order Issued | Work Completed
 | 0 | 1 | 7 | 1 | 1
 | 0 | 440 | 1041.71 | 4.05 | 0.82
Chart: Mobility and Social sector
| DPR under Preparation | DPR approved | Tender Issued | Work Order Issued | Work Completed
 | 0 | 1 | 7 | 1 | 1
 | 0 | 440 | 1041.71 | 4.05 | 0.82
PROJECT STATUS -CSCL
Chart: Water, Waste Water and Sanitation
| DPR under Preparation | DPR approved | Tender Issued | Work Order Issued | Work Completed
 | 0 | 1 | 7 | 1 | 1
 | 0 | 440 | 1041.71 | 4.05 | 0.82
Chart: Urban retrofit and Redevelopment
| DPR under Preparation | DPR approved | Tender Issued | Work Order Issued | Work Completed
 | 0 | 1 | 7 | 1 | 1
 | 0 | 440 | 1041.71 | 4.05 | 0.82
Tender Issued
Work Order Issued
Work Completed
DPR Approved
DPR under Preparation

## Slide 5
Augmentation of Sewerage Treatment Plants (STPs)
Features
100% treatment of Sewage
Most stringent parameters being followed for treatment
Processed Water fit for reuse
BOD <= 5mg/litre
More Energy Efficient.
Risk to public health & env.
Total Project Cost: 855 Cr.
Total Tender Cost: 556 Cr.
Stage: Tender to be reissued after splitting it in 3 packages
Reissue of tender: 15 Feb
Award of Project:15 May
S. No | Location | Capacity (MGD) |  | Technology |  | Remarks
 |  | Existing | Proposed | Existing | Proposed | 
1 | Diggian | 30 | 30 | MBBR | Open Technology to meet the functional guarantees & desired parameter | New plant(s) will be constructed
2 | Raipur Kalan | 5 | 5 | UASB |  | 
3 | Raipur Khurd | 1.25 | 2 | ASP |  | 
4 | 3 BRD | 11 | 11 | SBR | - | Additional units to be added
5 | Dhanas | 1.65 | 1.65 | SBR | - | 
6 | Raipur Kalan* | 1.25 | 1.25 | SBR | - | Not Commissioned
7 | STP at Maloya* | 5 | 5 | SBR | - | Commissioned
Total (MGD) |  | 55.15 | 55.9 |  |  | 
*New STPs Constructed by Municipal Corporation

## Slide 6
Augmentation of Sewerage Treatment Plants (STPs)
3 BRD STP
Diggian STP
Raipur Kalan STP
Raipur Khurd STP
Dhanas STP

## Slide 7
Integrated Command Control Centre
Work Progress Financial Proposal and Draft Agreement from BEL expected today Cost of Project: Rs 239 Cr Signing of Agreement by Jan 2020 Project Implementation Timeline – January 2021 | 
CCTV
Dynamic
Messaging
Signs
City Network
ICCC
Traffic Enforcement
Traffic Signals
Monitoring
MCC Mobile App
Assets Mgmt
GIS
ITS
City Traffic Surveillance

## Slide 8
e-Governance Project
Citizen Related –Services dealing with citizens
at present operating manually (14 services).
Internal Services –Services of MC Chandigarh helping with day to day working (14 services).
Phase I -Web Portal & Mobile app, live by Jan’ 20
Phase II- Citizen related services including OBPS, live by Mar’ 20
Phase III- All Internal services, live by June 2020
Project Cost: 11.5 Cr.
Stage: Work in Progress
Fire services
Trade and marketing license
Booking of Banquet Hall / Community Hall
Store Management
Financial Accounting
AUDIT
Legal
Select Services

## Slide 9
Particulars | Project Details
Name of the Project | 24 x 7 Water Supply Manimajra- Pilot Project
Scope of Work | Project Area- 855.26 acres Capacity of UGR= 4 MG Capacity of OHSR= 1.29 MG Water requirement – 8MGD Length of Pipeline= 20 KM (Approx)
Proposed Components | Construction of UGR, OHSR Installation & Upgradation of Existing Pumping Machinery Laying of Pipeline Installation and Implementation of SCADA Installation of Smart meter
Proposed Mode | Design Built Operate
24x7 WATER SUPPLY (MANIMAJRA)
Construction of UGR, OHSR
Installation & Upgradation of Existing Pumping Machinery
Retrofitting of existing Pipeline Network.
Installation and Implementation of SCADA
Smart Metering
CAPEX: 71.10 CR
OPEX : 91.96 CR.(15 years)
Total Cost 163.06 Cr.
Tender to Be reissued
Target date of Tender: 28/02/2020
Target date of Award: 01/06/2020
Components
Notes: Ensure safe and equitable water supply around the clock (24x7) to all households in Manimajra,
Reduce the overall consumption of water by reducing water losses as well as NRW,
Ensuring to bring about 100% recovery of water charges,
Improve and augment the economic and social infrastructure,
Making sure the technical and economical sustainability of the water supply service.

## Slide 10
24x7 WATER SUPPLY (PILOT)
Construction of UGR, OHSR
Installation & Upgradation of Existing Pumping Machinery
Retrofitting of existing Pipeline Network.
Installation and Implementation of SCADA
Smart Metering
CAPEX: 71Cr
OPEX : 92 Cr.(15 years)
Total Cost 163 Cr.
Tender reissued date : 28/02/2020
Target date of Award: 01/06/2020
Components
Project Area- 855.26 acres
Capacity of UGR= 4 MG
Capacity of OHSR= 1.29 MG
Water requirement of Area – 8MGD
20 km pipeline being replaced
MANIMAJRA

## Slide 11
24x7 WATER SUPPLY (PAN CITY)
Construction of new UGRs
Upgradation of Existing Pumping Machinery to Variable Frequency Derive Pumps (VFDs).
Retrofitting of existing Pipeline Network.
100% AMR Ready water metering
Installation of SCADA System
Effective DEMAND -SUPPLY MANAGEMENT
Leak detection services, UfW reduction to <15%
Components
CAPEX: Rs 440 Cr (Loan : ~Rs 360 Cr)
OPEX : 3125.57 CR.
Funding being sought from AfD
DPR approved by Board
To be sent to DEA for approval
Loan approval Expected by December 2020

## Slide 12
Removal of public nuisance
Reclamation of 16 Acres of Urban Land
Reduction in Foul Odour for nearby Colonies
Impact
PROJECT COMPONENT
Cleaning of 5 Lakh MT of Dump proposed over next 18 months Through Waste Mining of 1200 Tonne/day
Legacy Waste Mining at Daddu Majra Dumping Site
Total Cost 33.98
Status : Under Implementation
Time period : 540 days
Expected date of completion: March 2021
Notes: Dispose off around 5,00,000 MT existing legacy waste from Daddu Majra Dumping Ground (DMDG) through scientific mining and processing by way of deploying suitable & adequate number of heavy earth moving machinery, processing equipment, transportation of segregated material and scientific treatment technology.
Minimize the nuisance to the residents of Daddumajra on account of the fugitive emission, spontaneous combustion, Leachate etc.
Reclaim the entire 25 acres land blocked with the dump for future use.
Methodology
    Excavation of Legacy waste from the dumping ground.
    Weighment, transportation and stacking of this waste into Windrows.
    Spraying Bio-culture and turning of waste in Windrows.
    Shifting of 7 day old waste from Windrows to processing unit lines.
    Treatment and Segregation of ingredients of waste and collection of end product.
    Disposal of segregated end product

## Slide 13
Public Bike Sharing System & Cycle Tracks
Largest PBS -Pan City Coverage Last mile connectivity with 5000 bikes & 617 Docks
No Financial implications-- PPP Mode
Bids Under Evaluation
Expected Date of Work Order: 15/02/2020
Approx 190 Km of Dedicated Cycle Track- Completed.
Features
Components
Intelligent Integrated Docks
Intelligent Command Control Centre
Back lit panels for advertisement & public
information dissemination

## Slide 14
Other Projects
Underground Utility Mapping Project Cost : Rs 6.0 Cr Work Progress 350 Km of survey completed out of 1550 Km | 
SCADA System (Tertiary Water) Work Progress Approval of Equipments under process Project Cost : Rs 4.0 Cr (with 5 year O&M) Completion: 10/10/2020
Implementation of Smart School in ABD
Total Cost 4.8 Cr.
Date of Completion of project: 16/04/2020
Basic Infrastructure for Smart Schools
Total Cost 0.5 Cr.
Date of Completion of project: 14/04/2020

## Slide 15
Urban Redevelopment and Retrofit -Sector 43
Rs. 4932 Cr (PPP Project)
Status: Project dropped from SCP as it was in forest land.
    City has requested MoHUA to revise the SCP project size in MIS
REQUEST FOR MoHUA

## Slide 16
Garbage Transfer Station cum Material Recovery Facility
Total 3 no. MRF-cum GTS proposed
Segregated wet and dry waste processing
Material recovery platform for segregation of reusable materials
Dry waste end product carried to RDF plant
Wet waste end product carried to Compost plant
Stage: Tenders Under Evaluation
  MRF cum GTS Station
  Purchase of Small Vehicle
Expected Date of award of work: 15/02/2020
Expected Date of completion of work: 15/08/2020
MRF-cum-GTS at 3 locations
SCADA
Purchase of small vehicles

## Slide 17
Environmental friendly disposal of animal carcasses
Omission of public nuisance due to unhygienic disposal of carcasses
Pollution (land and air)control
Impact
INCINERATOR FOR ANIMAL CARCASS
Proposed Mode | Design and Built with 5 years AMC
CAPEX & OPEX | Estimated Project Cost:-Rs. 1.8 Cr.
Project Status Expected Work Order Issue :15th Feb 2020 | 

## Slide 18
Particulars | Project Details
Project Location | Pan City
Project Components | Design, Build Operate and transfer of Engineered Sanitary Landfill Facilities for Municipal Solid Waste in Chandigarh are proposed to be implemented with private participation under a Build-Operate-Transfer (BOT) Concession framework for a concession period of 27 yrs. out of which 12 years active operation and 15 years post closure period.
CAPEX & OPEX | Estimated Project Cost:- Rs. 30Crore
Project Status | DPR under Preparation
Construction and Management of Sanitary landfill